PROJECT BUDGET AND WORK PLAN

Part 1: Budget Summary

1.1 Three-Year Financial Overview

| Year | Total Cost | Estimated Benefits | Net Value | ROI |
| --- | --- | --- | --- | --- |
| Year 1 | $111,320 | $400,000 | $288,680 | 259% |
| Year 2 | $100,590 | $450,000 | $349,410 | 347% |
| Year 3 | $100,590 | $500,000 | $399,410 | 397% |
| 3-Year Total | $312,500 | $1,350,000 | $1,037,500 | 332% |

## 1.2 Year 1 Pilot Deployment Budget (Detailed)

| Category | Item | Specification | Cost (USD) |
| --- | --- | --- | --- |
| Infrastructure | Cloud hosting | 12 months @ $300/mo | $3,600 |
|  | Backup and SSL certificates | Annual | $800 |
| Software | Twitter Academic API | Free tier | $0 |
|  | Python, PostgreSQL, scikit-learn | Open source | $0 |
| Personnel - Technical | System Administrator | 0.5 FTE, $60,000/year | $30,000 |
|  | Data Engineer | 0.25 FTE, $72,000/year | $18,000 |
| Personnel - Analytical | Epidemiologist | 0.25 FTE, $96,000/year | $24,000 |
|  | Public Health Analyst | 0.2 FTE, $60,000/year | $12,000 |
| Personnel - Support | Tweet labelers | 520 hours, $15/hour | $7,800 |
| Training | Staff training & capacity building | One-time investment | $5,000 |
| Contingency | Contingency fund (10%) | 10% buffer | $10,120 |
|  | YEAR 1 TOTAL |  | $111,320 |

## 1.3 Ongoing Annual Budget (Years 2-3)

| Category | Description | Annual Cost (USD) |
| --- | --- | --- |
| Infrastructure | Cloud hosting + backup + SSL | $4,400 |
| Technical Staff | System Admin (0.5 FTE) + Data Engineer (0.25 FTE) | $48,000 |
| Analytical Staff | Epidemiologist (0.25 FTE) + Analyst (0.2 FTE) | $36,000 |
| Support Staff | Tweet labelers (260 hours/year, $15/hr.) | $3,900 |
| Maintenance | System updates, improvements, training | $3,500 |
| Contingency | 5% buffer | $4,790 |
|  | ANNUAL TOTAL (Years 2-3) | $100,590 |

## 1.4 Scale-Up Deployment Scenarios

| Deployment Model | Coverage | Staffing | Year 1 Cost |
| --- | --- | --- | --- |
| Pilot (Baseline) | 1 disease, 1 region | 1.4 FTE | $111,320 |
| Multi-Disease | 3 diseases, 1 region | 2.0 FTE | $145,000 |
| Regional Network | 1 disease, 5 regions | 2.5 FTE | $192,000 |
| Comprehensive | 3 diseases, 5 regions | 3.5 FTE | $245,000 |

## 1.5 Cost Breakdown by Category (Year 1)

| Category | Amount | Percentage of Total |
| --- | --- | --- |
| Personnel (all staff) | $91,800 | 82.5% |
| Infrastructure and Software | $4,400 | 4.0% |
| Training | $5,000 | 4.5% |
| Contingency | $10,120 | 9.1% |
| TOTAL | $111,320 | 100.0% |

82.5% of costs are personnel. Infrastructure is only 4%, making this system highly affordable with no expensive hardware requirements.

# Part 2: Implementation of Work Plan

## 2.1 12-Month Phased Implementation Roadmap

| Phase | Timeline | Key Activities | Deliverables |
| --- | --- | --- | --- |
| Phase 1: Preparation | Months 1-2 | • Procure cloud infrastructure • Set up development environment • Hire/train staff • Establish data collection protocols • Configure Twitter API access | • Operational infrastructure • Trained team • Initial data pipeline |
| Phase 2: Pilot Testing | Months 3-4 | • Deploy in observation mode • Run parallel to existing surveillance • Label tweets manually for validation • Tune alert thresholds • Conduct retrospective comparison | • Validated alert thresholds • Performance baseline • Refined model |
| Phase 3: Active Surveillance | Months 5-8 | • Switch to operational mode • Generate daily alerts • Epidemiologist review workflow • Weekly model retraining • Continuous monitoring | • Daily outbreak alerts • Documented response actions • Performance logs |
| Phase 4: Evaluation and Expansion | Months 9-12 | • Comprehensive performance review • Document lessons learned • Prepare scale-up plan • Stakeholder presentations • Budget planning for Year 2 | • Evaluation report • Scale-up proposal • Year 2 budget |

## 2.2 Detailed Activity Timeline (Months 1-12)

| Activity | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Infrastructure setup | █ | █ |  |  |  |  |  |  |  |  |  |  |
| Staff recruitment & training | █ | █ |  |  |  |  |  |  |  |  |  |  |
| Data pipeline development | █ | █ | █ |  |  |  |  |  |  |  |  |  |
| Initial model training |  | █ | █ |  |  |  |  |  |  |  |  |  |
| Pilot testing (observation mode) |  |  | █ | █ |  |  |  |  |  |  |  |  |
| Alert threshold tuning |  |  |  | █ | █ |  |  |  |  |  |  |  |
| Operational deployment |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ |
| Weekly model retraining |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ |
| Performance monitoring |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ |
| Mid-term review |  |  |  |  |  | █ | █ |  |  |  |  |  |
| Final evaluation |  |  |  |  |  |  |  |  |  |  | █ | █ |
| Year 2 planning |  |  |  |  |  |  |  |  |  | █ | █ | █ |

Legend: █ = Active period for this activity

## 2.3 Staffing Requirements and Responsibilities

| Role | FTE | Key Responsibilities | Start Month | Annual Cost |
| --- | --- | --- | --- | --- |
| System Administrator | 0.5 | Infrastructure management, system monitoring, security updates | Month 1 | $30,000 |
| Data Engineer | 0.25 | Data pipeline maintenance, API integration, database optimization | Month 1 | $18,000 |
| Epidemiologist | 0.25 | Alert review, clinical validation, threshold adjustment | Month 2 | $24,000 |
| Public Health Analyst | 0.2 | Dashboard monitoring, report generation, stakeholder communication | Month 3 | $12,000 |
| Tweet Labelers (part-time) | Variable | Manual tweet labeling for ongoing model improvement (10 hrs/week) | Month 5 | $7,800 |

# Part 3: Potential Funding Sources

| Funding Source | Type | Typical Amount | Application Timeline |
| --- | --- | --- | --- |
| Government Health Budgets | Direct allocation | Full coverage ($111K) | Annual budget cycle |
| NIH/CDC Research Grants | Competitive grant | $100K - $500K | 6-12 months |
| WHO Disease Surveillance Programs | International funding | $150K - $300K | 9-12 months |
| Gates Foundation | Philanthropic grant | $200K - $500K | 12-18 months |
| Wellcome Trust | Research funding | $100K - $400K | 9-15 months |
| USAID Global Health Security | Development aid | $150K - $600K | 12-24 months |
| Emergency Preparedness Funds | Rapid deployment | $100K - $250K | 3-6 months |
| Public-Private Partnerships | Mixed funding | Variable (50%-100%) | Negotiable |

Part 4: Budget Risks and Mitigation Strategies

| Risk | Probability | Impact on Budget | Mitigation Strategy |
| --- | --- | --- | --- |
| Difficulty recruiting qualified staff | Medium | +$10K-$20K for higher salaries | Partner with universities; use contract staff initially |
| Twitter API cost increases | Low | +$5K-$15K/year | Switch to free tier; reduce data collection frequency |
| Scope creep (multi-disease) | High | +$30K-$50K | Strict phase gates; separate funding for expansion |
| Cloud infrastructure overruns | Low | +$2K-$5K | Monitor usage closely; optimize storage |
| Training needs exceed estimate | Medium | +$3K-$8K | Use online training; internal knowledge transfer |
| Currency fluctuations (if non-USD) | Low | ±5-10% | Budget in local currency; maintain reserves |

# Summary

Total Investment Required: $111,320 (Year 1) | $100,590/year (Years 2-3)

Implementation Timeline: 12 months from start to operational deployment

Expected ROI: 259% Year 1 | 332% cumulative over 3 years

Primary Cost Driver: Personnel (82.5% of budget)

Key Budget Advantage: No expensive hardware, no proprietary software licenses, standard cloud infrastructure.

This budget and work plan provides a realistic framework for pilot deployment. All figures are based on validated cost estimates from Chapter 5. Actual costs may vary by ±10-15% depending on local conditions, staffing availability, and specific implementation choices.